## Official
Incident No | CR/Issue Description | Stage | To Do | Start Date | Assigned Date | Age | Expected Resolution Date | Time Left | Resolution Date | Resolution Day | User | Status
SR00476097 | A report from MES database is needed, containing information about the inventory that summarizes quantities plant per inventory status OR per storage locations(warehouse) and inventory status in one line in order to make more effective the inventory control work in materials management. |  |  | 2019-04-01 | 2019-04-01 | 24 | 2019-04-11 | -14 |  |  | Blanca Marqués | Open
SR00486520 | Remove all pick lists from the KNEE facility that has A) Started -status and B) has a start date before 1.4.2019. Total amount of records to be deleted should be 936. |  |  | 2019-04-11 | 2019-04-11 | 14 | 2019-04-21 | -4 |  |  | Jani Mononen | Open
IN00478847 | Slowness in goods receiving. We cannot take material effectively. Reception is congested. Production does not get material. |  |  | 2019-04-03 | 2019-04-17 | 22 | 2019-04-24 | -1 |  |  | Janne Luukkonen | Open
IN00480648 | During the uploading orderbound material has lost sales order bonding. See document attached, |  |  | 2019-04-05 | 2019-04-09 | 20 | 2019-04-26 | 1 |  |  | Margarita Gonzalez | Open
IN00480670 | It seems that during inventory upload all order bound materials have lost their bonding information. Why this has happened? see attaché file of order bound materials and look at also IVL |  |  | 2019-04-05 | 2019-04-09 | 20 | 2019-04-26 | 1 |  |  | Vesa Sarja | Open
IN00485793 | We have tried pack following production orders 11193656 11193651 11193652 We get error message (see attachment file). |  |  | 2019-04-10 | 2019-04-11 | 15 | 2019-05-01 | 6 |  |  | Janne Luukkonen | Open
IN00486608 | Packing item lists are needed from the boxes: B8237155.1000 B8237155.1001 B8237155.1002 B8237155.1003 B8237155.1004 B8237155.1005 B8237155.1006 |  |  | 2019-04-11 | 2019-04-09 | 14 | 2019-05-02 | 7 |  |  | Olli Koskelo | Closed
POE_M | Developing a new screen with multiple Start and Confirm. |  |  |  | 2019-04-18 | [6 empty] | Open
IN00498644 | The MES SQL report is quite strange, sometimes it took more than 5 minutes to execute it, normally happen in the morning for nearly everyday the first time to run the report. and after if I run it again and again, it is so fast and can list the result in 30 seconds. |  |  | 2019-04-25 | 2019-04-25 | 0 | 2019-05-16 | 21 |  |  | Chao, Leon Li | Open
Formulas:
Age = TODAY() - [Start Date]
Time Left = [Expected Resolution Date] - TODAY()