## Official
Incident No | CR/Issue Description | Remarks | To Do | Start Date | Assigned Date | Age | Expected Resolution Date | Time Left | Resolution Date | Resolution Day | User | Status
SR00476097 | A report from MES database is needed, containing information about the inventory that summarizes quantities plant per inventory status OR per storage locations(warehouse) and inventory status in one line in order to make more effective the inventory control work in materials management. | Development feasibility tested. Have mailed Blanca for COE approval. |  | 2019-04-01 | 2019-04-01 | 21 | 2019-04-11 | -11 |  |  | Blanca Marqués | Open
SR00486520 | Remove all pick lists from the KNEE facility that has A) Started -status and B) has a start date before 1.4.2019. Total amount of records to be deleted should be 936. | No work so far. | 1. Follow up with Subhash | 2019-04-11 | 2019-04-11 | 11 | 2019-04-21 | -1 |  |  | Jani Mononen | Open
IN00478847 | Slowness in goods receiving. We cannot take material effectively. Reception is congested. Production does not get material. | No work so far. | 1. Ask for mail with Sneha. | 2019-04-03 | 2019-04-17 | 19 | 2019-04-24 | 2 |  |  | Janne Luukkonen | Open
IN00480648 | During the uploading orderbound material has lost sales order bonding. See document attached, | Issue explained. Not satisfied. | 1. Check SOs which are given exist or not in system. 2. Check whether not present SOs are uploaded or not. | 2019-04-05 | 2019-04-09 | 17 | 2019-04-26 | 4 |  |  | Margarita Gonzalez | Open
IN00480670 | It seems that during inventory upload all order bound materials have lost their bonding information. Why this has happened? see attaché file of order bound materials and look at also IVL | Issue explained. Not satisfied. |  | 2019-04-05 | 2019-04-09 | 17 | 2019-04-26 | 4 |  |  | Vesa Sarja | Open
IN00485793 | We have tried pack following production orders 11193656 11193651 11193652 We get error message (see attachment file). | Issue explained. Not satisfied. |  | 2019-04-10 | 2019-04-11 | 12 | 2019-05-01 | 9 |  |  | Janne Luukkonen | Open
IN00486608 | Packing item lists are needed from the boxes: B8237155.1000 B8237155.1001 B8237155.1002 B8237155.1003 B8237155.1004 B8237155.1005 B8237155.1006 | Handed over to Prutvij. |  | 2019-04-11 | 2019-04-09 | 11 | 2019-05-02 | 10 |  |  | Olli Koskelo | Closed
POE_M | Developing a new screen with multiple Start and Confirm. | No work so far. |  |  | 2019-04-18 | [6 empty] | Open
Formulas:
Age = TODAY() - [Start Date]
Time Left = [Expected Resolution Date] - TODAY()